## TraceabilityMatrix
requirement index | development status | requirement description | test plan index | test plan title | test description index | test description title | test Status | test date | software design index | software design title
3.1.1 | Done | The system shall provide user authentication. | 5.2.1.1 | User Login Customer Acceptance Tests | 4.3 | pytest.Login | Pass | 2016-03-08 | 3.1.1.3 | AccountController
3.1.1.1 | Done | The users shall belong to one of the following roles. | 5.2.1.1 | User Login Customer Acceptance Tests | N/A | N/A | N/A | N/A | 3.1.1.3 | AccountController
3.1.1.1.1 | Done | Patient | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3.1.1.1.1.1 | Done | At a minimum, the system shall store the following information about a patient accounts: unique patient id, username, password, age, weight, height, race, gender, and account status (enabled/disabled). | 5.2.1.2 | User Information Tests | 4.1.3 | Create Patient | Pass | 2016-03-08 | 3.2.1.5 | Patient
3.1.1.1.1.2 | Done | The system shall prevent any personal identifiable information from being available for a Patient | 5.2.1.3 | User Privacy Tests |  |  |  |  | 3.2.1.5 | Patient
3.1.1.1.1.3 | Done | The system shall only allow a Patient to view their data. | 5.2.1.1 | User Login Customer Acceptance Tests | 4.5.1 | Patient to Patient |  |  | 3.1.1.8 | PatientController
3.1.1.1.2 | Done | Physician | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3.1.1.1.2.1 | Done | At a minimum, the system shall store the following information about physician accounts: unique physician id, e-mail address, username, password, and account status (enabled/disabled). | 5.2.1.2 | User Information Tests | 4.1.1 | Create Physician | Pass | 2016-03-08 | 3.2.1.6 | Physician
3.1.1.1.2.2 | Done | The system shall allow a physician user to update the attributes associated with their account including e-mail address and password. | 5.2.1.4 | Account editing Tests | 4.2.1 | Physician can edit his account |  |  | 3.1.1.3 | AccountController
3.1.1.1.2.3 | Partial | The system shall allow the physician user to view their patient’s data graphically. | 5.2.1.20 | Graph View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.1.1.2.4 | Done | The system shall allow physician users to view only the data associated with their patients. | 5.2.1.1 | User Login Customer Acceptance Tests | 4.5.2 | Physician to patient |  |  | 3.1.1.6 | PhysicianController
3.1.1.1.2.5 | Done | The system shall allow only a physician user to add a patient to the system. | 5.2.1.1 | User Login Customer Acceptance Tests | 4.1.3 | Create Patient | Pass | 2016-03-08 | 3.1.1.6 | PhysicianController
3.1.1.1.2.6 | Review | The system shall allow a physician user to delete their patients from the system. | 5.2.1.1 | User Login Customer Acceptance Tests | 4.1.4 | Delete patient | Pass | 2016-03-08 | 3.1.1.6 | PhysicianController
3.1.1.1.3 | Done | Experiment Administrator | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3.1.1.1.3.1 | Done | At a minimum, the system shall store the following information about experiment administrator accounts: unique experiment administrator id, e-mail address, username, password, and account status (enable/disable). | 5.2.1.2 | User Information Tests | 4.1.2 | Create Experiment Admin |  |  | 3.2.1.7 | ExperimentAdministrator
3.1.1.1.4 | Done | System Administrator | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3.1.1.1.4.1 | Done | At a minimum, the system shall store the following information about system administrator accounts: unique system administrator id, e-mail address, username, password, and account status (enable/disable). | 5.2.1.2 | User Information Tests |  |  |  |  | 3.2.1.4 | AspNetUser
3.1.1.1.4.2 | Done | System Administrators shall have the ability to enable, disable, add, and remove all users except patients. | 5.2.1.5 | Account Management Tests | 4.1.1 | Create Physician | Pass | 2016-03-08 | 3.1.1.5 | AdminEditController
3.1.1.1.4.3 | Done | System administrators shall have the ability to reset passwords. | 5.2.1.9 | Username/Password Retrieval Tests | 4.4.6 | Reset Password | Pass | 2016-03-08 | 3.1.1.5 | AdminEditController
3.1.1.1.4.4 | Review | System administrators shall be able to update physician, patient and experiment administrator account information. | 5.2.1.4 | Account editing Tests | 4.2.2 | Sys Admin can edit patient account |  |  | 3.1.1.5 | AdminEditController
3.1.1.2 | Done | The system shall require unique usernames for each registered user. | 5.2.1.6 | Username Tests | 4.7.1 | Username cannot be copied | Pass |  | 3.1.1.3 | AccountController
3.1.1.2.1 |  | Usernames will be changeable as long as the username remains unique. | 5.2.1.6 | Username Tests | 4.7.1 | Username cannot be copied
3.1.1.3 | Done | The system shall assign unique ids to each created patient. | 5.2.1.7 | Patient ID Tests |  |  |  |  | 3.1.1.3 | AccountController
3.1.1.3.1 | Done | The system shall display the patient id to the user that created the patients so that the user can keep a record of which patient corresponds to which id after account creation. | 5.2.1.7 | Patient ID Tests | 4.1.3 | Create Patient | Pass | 2016-03-08 | 3.1.1.3 | AccountController
3.1.1.4 | Done | The system shall require a user account to have a password that meets minimum security criteria. | 5.2.1.8 | Password Tests | 4.4.1 | Create Physician | Pass | 2016-03-08 | 3.1.1.3 | AccountController
3.1.1.4.1 | Done | The system shall require the passwords to be a miniumum of 10 characters in length. | 5.2.1.8 | Password Tests | 4.4.2 | Password Length | Pass | 2016-03-08 | 3.1.1.3 | AccountController
3.1.1.4.2 | Done | The system shall require the password to contain at least one uppercase and one lowercase letter. | 5.2.1.8 | Password Tests | 4.4.3 | Password Case | Pass | 2016-03-08 | 3.1.1.3 | AccountController
3.1.1.4.3 | Done | The system shall require the password to contain at least one number. | 5.2.1.8 | Password Tests | 4.4.4 | Password Digit | Pass | 2016-03-08 | 3.1.1.3 | AccountController
3.1.1.4.4 | Done | The system shall require the system to contain at least one special character. | 5.2.1.8 | Password Tests | 4.4.5 | Password Special Char | Pass | 2016-03-08 | 3.1.1.3 | AccountController
3.1.1.5 | Done | The user shall have the ability to log out of their account. | 5.2.1.1 | User Login Customer Acceptance Tests | 4.3.1 | Login Physician | Pass | 2016-03-08 | 3.1.1.3 | AccountController
3.1.1.6 |  | The system will have a utility for retrieving a forgotten username or password. | 5.2.1.9 | Username/Password Retrieval Tests
3.1.1.7 | Done | The system shall allow Physicians and Experiment Administrators to create their own accounts. | 5.2.1.5 | Account Management Tests | 4.1.1 | Create Physician | Pass | 2016-03-08 | 3.1.1.3 | AccountController
3.1.1.7.1 | Done | The system shall require a system administrator to verify the creation of a new Physician or Experiment Administrator. | 5.2.1.5 | Account Management Tests | 4.1.1 | Create Physician | Pass | 2016-03-08 | 3.1.1.4 | AdminHomeController
3.1.1.7.2 | Done | Physicians shall create the accounts of their patients. | 5.2.1.5 | Account Management Tests | 4.1.3 | Create Patient | Pass | 2016-03-08 | 3.1.1.6 | PhysicianController
3.1.2 | Partial | The system shall provide the ability to process medical device data files. | 5.2.1.11 | File Upload Interface Tests | 4.6 | Pytest.Upload |  |  | 3.1.1.1 | SelectDataController
3.1.2.1 | Done | The system shall process multiple files at the same time or a single file. | 5.2.1.10 | Data File Processing Interface Tests | 4.6.2 | Multi File No Activity |  |  | 3.1.1.1 | SelectDataController
3.1.2.2 |  | The system shall provide the ability to assign an activity (ex. running, walking, sleeping) to the data by date and time. | 5.2.1.10 | Data File Processing Interface Tests | 4.6.3 | Single File One Activity |  |  | 3.1.1.2 | SelectActivityController
3.1.2.3 |  | The system shall give the user an interface to select which files to process and assign an activity to. | 5.2.1.11 | File Upload Interface Tests | 4.6.3 | Single File One Activity |  |  | 3.1.1.1 | SelectDataController
3.1.2.4 |  | The system will not process data that is not medical data. | 5.2.1.10 | Data File Processing Interface Tests |  |  |  |  | 3.1.1.1 | SelectDataController
3.1.2.5 | Done | The system shall process comma-separated values (.csv) files for each of the supported devices. | 5.2.1.12 | Data Type Tests | 4.6.2 | Multi File No Activity |  |  | 3.1.1.1 | SelectDataController
3.1.2.6 |  | The system will process raw data (.dat) files for each of the supported devices. | 5.2.1.12 | Data Type Tests | 4.6.7 | Zephyr Data Upload |  |  | 3.1.1.1 | SelectDataController
3.1.3 | Done | The system shall connect to a database. | 5.2.1.13 | Database Function Test |  |  |  |  | 3.1.1.2 | SelectDataController
3.1.3.1 | Partial | The system shall upload the processed data to the database. | 5.2.1.13 | Database Function Test |  |  |  |  | 3.1.1.2 | SelectDataController
3.1.4 | Done | The system shall allow experiments to be created. | 5.2.1.14 | Experiment Tests |  |  |  |  | 3.1.1.7 | ExperimentController
3.1.4.1 | Done | Experiments shall only be created by an experiment administrator. | 5.2.1.14 | Experiment Tests |  |  |  |  | 3.1.1.7 | ExperimentController
4.1.4.1.1 | Done | Experiment administrators shall have the ability to save the experiments that they have created. | 5.2.1.14 | Experiment Tests |  |  |  |  | 3.1.1.7 | ExperimentController
4.1.4.2 |  | Experiment results shall be viewable by experiment administrators and physicians. | 5.2.1.14 | Experiment Tests |  |  |  |  | 3.1.1.7 | ExperimentController
4.1.4.3 | Done | The system shall provide Experiment Administrators with a query builder used to create experiments. | 5.2.1.14 | Experiment Tests |  |  |  |  | 3.1.1.7 | ExperimentController
4.1.4.4 |  | The system shall allow Experiment Administrators and System Administrators to delete experiments. | 5.2.1.14 | Experiment Tests |  |  |  |  | 3.1.1.7 | ExperimentController
3.1.5 |  | The system shall allow data exporting. | 5.2.1.15 | Data Exportation Tests |  |  |  |  | 3.1.1.6, 3.1.1.7, 3.1.1.8 | Physician Controller Experiment Controller Patient Controller
3.1.5.1 |  | The system shall allow experiment results to be exported. | 5.2.1.15 | Data Exportation Tests |  |  |  |  | 3.1.1.7 | Experiment Controller
3.1.5.1.1 |  | The system will export experiment result graphs. | 5.2.1.15 | Data Exportation Tests |  |  |  |  | 3.1.1.7 | Experiment Controller
3.1.5.2 |  | The system shall allow patients to export their data. | 5.2.1.15 | Data Exportation Tests |  |  |  |  | 3.1.1.8 | Patient Controller
3.1.5.3 |  | The system shall allow physicians to export the data of their patients. | 5.2.1.15 | Data Exportation Tests |  |  |  |  | 3.1.1.6 | Physican Controller
3.1.5.4 |  | The system shall provide comma-separated values (.csv) file exports. | 5.2.1.15 | Data Exportation Tests |  |  |  |  | 3.1.1.6, 3.1.1.7, 3.1.1.8 | Physician Controller Experiment Controller Patient Controller
3.1.6 | Done | The system shall provide account management. | 5.2.1.5 | Account Management Tests |  |  |  |  | 3.1.1.3 | AccountController
3.1.6.1 | Done | The system shall allow account creation. | 5.2.1.5 | Account Management Tests | 4.1.1 | Creat Physician | Pass | 2016-03-08 | 3.1.1.3 | AccountController
3.1.6.1.1 | Done | The system shall force account creation approval for both physicians and experiment administrators before their accounts become active for use. | 5.2.1.5 | Account Management Tests | 4.1.1 | Creat Physician | Pass | 2016-03-08 | 3.1.1.3 | AccountController
3.1.6.1.2 | Done | Patients shall not need approval at the time of account creation, since they are created by an approved physician. | 5.2.1.5 | Account Management Tests | 4.1.3 | Create Patient | Pass | 2016-03-08 | 3.1.1.3 | AccountController
3.1.6.2 | Done | The system shall allow users to edit account information. | 5.2.1.4 | Account editing Tests | 4.2.1 | Physician can edit his account |  |  | 3.1.1.3 | AccountController
3.1.6.3 | Review | The system shall allow only the system administrator to delete accounts. | 5.2.1.5 | Account Management Tests | 4.1.5 | Delete Physician | Pass | 2016-03-08 | 3.1.1.5 | AdminEditController
3.1.6.4 | Done | Only a system administrator shall have the ability to enable accounts. | 5.2.1.5 | Account Management Tests |  |  |  |  | 3.1.1.5 | AdminEditController
3.1.6.5 | Done | Only a system administrator shall have the ability to disable accounts. | 5.2.1.5 | Account Management Tests |  |  |  |  | 3.1.1.5 | AdminEditController
3.1.7 | Done | The system shall provide a user interface for displaying medical data in the system. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.1 | Partial | The system shall provide a graphical display of accelerometer data. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.2 | Done | The system shall provide a graphical display of breathing rate. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.2.1 | Partial | This following additional information regarding heart rate and ECG will be displayed if available: amplitude, noise, and data confidence. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.3 | Partial | The system shall provide a graphical display of heart rate and ECG data. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.3.1 | Partial | This following additional information regarding heart rate and ECG will be displayed if available: amplitude, noise, data confidence, and heart rate variability. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.3.2 |  | Breath to Breath intervals shall be displayed. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.3.3 |  | Beat to Beat intervals shall be displayed. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.4 |  | The system shall provide a graphical display of skin temperature. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.5 |  | The system shall provide a graphical display of an activity measurement. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.6 |  | The system shall provide a graphical display of peak acceleration. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.7 |  | The system shall provide a graphical display of posture data. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.8 |  | The system shall provide a graphical display of Galovanic skin resistance. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.9 |  | The system shall provide a graphical display of calorie data. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.10 |  | The system shall provide a graphical display of steps. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.11 |  | The system will provide a graphical display of gyroscope data. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.12 |  | The system shall provide a graphical display of UV index data. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.13 |  | The system shall provide a graphical display of speed data. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.14 |  | The system shall provide a graphical display of pace data. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.1.7.15 |  | The system will display Zephyr event data. | 5.2.1.16 | Medical Data View Tests |  |  |  |  | 3.1.1.6 | PhysicianController
3.2.1 | Done | The system shall run on Windows Server Operating System | 5.2.1.17 | OS Test |  |  |  |  | N/A | N/A
3.2.2 | Done | The system shall use a SQL database. | 5.2.1.18 | SQL Database Test |  |  |  |  | N/A | N/A
3.2.3 | Done | The system shall require a server to be connected to a network with an internet connection. | 5.2.1.19 | Network Connection Test |  |  |  |  | N/A | N/A
3.2.4 |  | The system shall support the data export from the following wearable medical devices. | 5.2.1.12 | Data Type Tests |  |  |  |  | 3.1.1.2 | SelectActivityController
3.2.4.1 | Done | Zephyr. | 5.2.1.12 | Data Type Tests | 4.6.7 | Zephyr Data Upload |  |  | 3.1.1.2 | SelectActivityController
3.2.4.2 | Done | BasisPeak | 5.2.1.12 | Data Type Tests | 4.6.1 | Single File No Activity |  |  | 3.1.1.2 | SelectActivityController
3.2.4.3 |  | Microsoft Band. | 5.2.1.12 | Data Type Tests | 4.6.8 | Mband Data Upload |  |  | 3.1.1.2 | SelectActivityController
[5 empty] | Test Development %: | 47.78%